## Logical framework
Joint Operational Programme Black Sea Basin 2007-2013
LOGICAL FRAMEWORK FOR THE ACTION
| Intervention | Objectively verifiable | Sources and means of |  | Assumptions
| logic | indicators of achievement | verification
Overall | What are the overall broader | What are the key indicators related | What are the sources of information for these indicators?
objectives | objectives to which the Action | to the overall objectives?
| will contribute? | Indicate the indicators' target value.
| General Obiective of the project is to work out and implement common policies in order to improve and protect the environment in partner-regions from the the Black Sea Basin, as a precondition for a sustainable economic development. | Increase of GDP of partner-countries; Increase of population's incomes; Growth of living standards; | Reports of the World Bank, studies in the field, Statistic Annuaries of partner-countries.
Specific | What specific objective is the | Which indicators clearly show | What are the sources of |  | Which factors and conditions outside
objective | Action intended to achieve to | that the objective of the | information that exist or can be |  | the Beneficiary's responsibility are
| contribute to the overall objectives? | Action has been achieved? | collected? What are the methods |  | necessary to achieve that objective? Which
|  | Indicate the indicators' target value. | required to get this information? |  | risks should be taken into consideration?
1 | Improvement of knowledge and experience in the field of efficient management of household wastes and of a wastes’ recycling system in partner-regions. | Modernization of the wastes' collecting, storing and recycling process in partner-regions, large-scale involvement of population in cleaning activities. The Study "Analysis of household wastes' impact on environment in the partner-regions" will be worked out; | Data from the reports of LPA, environmental institutions, materials from mass-media, information of the environmental NGOs. |  | Establishment of good relationships and contacts with institutions relevant to the field.
2 | Working out a Joint Action Plan of partners for environment protection in the Black Sea Basin. | A Joint Action Plan on environment protection in the Black Sea Basin; | Partnership Agreement signed by all 4 project-partners; The Joint Action Plan on environment protection in the Black Sea Basin translated into national languages of the partner-countries. |  | Maintenance of good relations between partners of the project.
3 | Raising the awareness of population from partner-regions on correct managing of household wastes and protection of rivers and environment in general. | Correct managing of wastes in domestic conditions; Active participation of members of Associations of Dwellers, population in cleaning actions; Joint Action Plan on environment protection in the Black Sea Basin. | Relevant data from environmental institutions and organizations, LPAs, Ecological State Inspectorate etc. Relevant information from the State Registration Chamber with regards to enterprises from Republic of Moldova. |  | Orientation to correct informing of population and awakening of citizens' interest towards the participation in the project's activities.
Expected | The results are the outputs envisaged to achieve | What are the indicators to measure whether and | What are the sources of |  | What external conditions must be met to
results | the specific objective.What are the expected results? | to what extent the Action achieves the expected | information for these indicators? |  | obtain the expected results on schedule?
| (enumerate them) | results? Indicate the indicators' target value.
1 | The level of sanitary and ecological culture of 200 participants in trainings will increase. | Lists with the number of participants. | Progres report, Narrative and Financial reports of the project staff. |  | Interest showed by the participants;
2 | 12 participants will take over good practices and advanced experience in wastes’ recycling will be acquired; | Lists of participants in study visit | Progres report, Narrative and Financial reports of the project staff. |  | Visas performed for participation in trainings from Romania.
3 | Proposals regarding operative actions for improvement of environmental situation will be formulated by specialized institutions; | Number of proposals and solutions included in Joint Action Plan for environment protection in the Black Sea Basin for the period 2012-2015 | Joint Action Plan for environment protection in the Black Sea Basin for the period 2012-2015 |  | Well-trained participants during work-shops.
4 | Operational framework for protection actions in order to improve environment situation in Black Sea Basin will be worked out. | Joint Action Plan for environment protection in the Black Sea Basin for the period 2012-2015 | Web-sites of LPAs from those 4 partner countries |  | Efficient collaboration of partners from 4 countries in order to work out the Joint Action Plan for environment protection in the Black Sea Basin for the period 2012-2015
5 | Permanent sources of environment’s pollution will be liquidated in all 4 partner-regions. | Reports of ecological and environmental institutions from 4 partner-regions. | Annuaries about the condition of environment; Statistic information about the condition of environment. |  | Interest showed by the society;
4
6 | Environmental problems in each partner-region will be identified and priorities defined; | Study "Analysis of household wastes' impact on environment in the partner-regions" | Replies from mass-media, photos; |  | Efficient collaboration of partners from 4 countries on working out the Study "Analysis of household wastes' impact on environment in the partner-regions"
7 | The ecologic situation of localities and population’s health in partner-regions will be improved. | Reports of ecological and environmental institutions from 4 partner-regions. | Anmuaries about the condition of environment; Statistic information about the condition of environment. |  | Companies specialized in the field.
8 | The level of professional competence of Utility Division’s employees will upgrade; | Lists of participants in trainings for employees of Utility Division from Republic of Moldova. | Replies from mass-media, photos; |  | Interest showed by the participants;
9 | The degree of entrepreneurs' professional training in the field of applying technologies for eco-products' production will increase. | Lists of participants in Training for eco-product production. | Progres report, Narrative and Financial reports of the project staff, photos. |  | Interest showed by the participants;
10 | Improvement of economic situation in partner regions as a result of taken over good practices in recycling of wastes with economic purposes. | Number of businesses initiated in applying technologies concerning eco-products' production and use of recyclable materials. | Information from the Business Registration Chambers. |  | Favourable economic and fiscal environment in partner countries.
11 | 80 participants informed about the Project's launching, thus being ensured the extension of project’s impact and increase of beneficiaries’ number | Lists of participants. | Progres report, Narrative and Financial reports of the project staff, photos. |  | Awarding of grant by the donor.
12 | 26 press-releases appeared and spread in local and national press from 4 partner countries. | Articles published in national and regional press in those 4 partner-countries. | Regional and local newspapers and magazines from those 4 countries. |  | Companies specialized in the field.
13 | 10 actiuni TV and Radio cu mesaje de sensibilizare ascultate si privite de populatia tarilor partenere; | TV and Radio programmes broadcasted. | TV and Radio recordings. |  | Companies specialized in the field.
14 | About 50 % of population from those four partner-countries will be informed about the necessity to manage correctly household wastes; | 100 copies of the Guide for employees of Utility Services, 4000 copies of the Project’s Folder, 12000 copies of the Folder “Measures of combating pollution” , 10000 copies of Flyers “To recycle correctly”; 6 banners with the project’s name, 45 copies of banners;10 TV and Radio broadcast; | Vouchers about distribution of publications and placing of banners, photos. |  | Companies specialized in the field.
15 | 60 de participants informed about the Project's accomplishment. Wide publicity of the project for the extension of its impact will be ensured; | Lists of participants. | Progres report, Narrative and Financial reports of the project staff, photos. |  | Companies specialized in the field.
16 | Sustainable partnership between project partners will be strengthened; | Number of organized sittings. | Progres report, Narrative and Financial reports of the project staff, photos. |  | Coordinated efforts and harmony in relationships between project partners and associates.
17 | The Project will be well administrated, will achieve its objectives, with an adequate reporting to the Contracting Authority; due to corresponding management; | Progress reports, monitoring visits, interim and final narrative and financial reports. | Progres report, Narrative and Financial reports of the project staff,photos.
18 | Partners’ capacities in management of environmental projects will be developed; | Evaluation report | Final evaluation report; |  | Companies specialized in the field.
19 | Premises for attraction of other funds in the field of environment protection will be created due to a qualified financial management. | Audit report | Final Audit report; |  | Companies specialized in the field.
What are the sources ofinformation about Action progress?
Progres, Interim and Final Reports
| What are the key activities to be carried out and in what sequence in order to | Means: What are the means required to implement these activities (personnel, | Costs: What are the Action costs? How are they classified? |  | What pre-conditions are required before the Action starts? What conditions outside
| produce the expected results? | equipment, training, studies, supplies, | Budget of the Action) |  | the Beneficiary's direct control have to be
|  | operational, facilities, travel, services, etc) |  |  | met for the implementation of the activities?
|  |  | TOTAL BUDGET | 587252.83
GA 1 | Activity 1.1: Training for population from Hincesti and Orhei, Moldova (members of Dwellers’ Association) | Articles in local, regional and national press | Total GA 1 | 125514.28 | Orientation to correct informing of population and awakening of citizens' interest towards the participation in the project's activities.
| Activity1.2: Study visit of Project partners to Romania | Implementing team of the Project | Travel | 16020 | Agreement of Embassies to issue visas.
| Activity 1.3: Focus-groups on the topic: „Healthy environment means our own health” | Companies providing transportation, accommodation, meal services | Subcontracted services | 43583 | Willingness of entreprises to develop new products and services
| Activity1.4: Elaboration of the Joint Action Plan for environment protection in the Black Sea Basin | Companies providing publishing services and promotional agencies | Administrative costs | 8211.22 | Coordinated efforts and harmony in relationships between project partners
| Activity1.5: Clean-up days “Think globally - act locally” | Building companies and a foreman, | Equipment and supplies | 8400 | The consent of LPA and environmental institutions concerning the selected plots for waste collecting points.
|  | Articles in local, regional and national press | Other | 49300,06 | Observance of contractual duties by the selected company in relation to the project.
GA 2 |  |  | Total GA 2 | 187960.86
| Activity 2.1 Study "Impact of household wastes on environment in partner-regions" | Companies providing advertising services | Travel | 18460 | Coordinated efforts and harmony in relationships between project partners.
| Activity 2.2 Improvement of infrastructure for wastes’ management in partner regions. | Building companies and a foreman | Equipment and supplies | 86000 | Interest showed by the society.
| Activity 2.3 Trainings for employees of Utility Division from Republic of Moldova. | National and international experts providing training services | Subcontracted services | 62640 | Proper selection of the material to be studied.
| Activity 2.4 Training ecoproduct | International experts providing training services | Other | 8564.36
| Activity 2.5 Business Ecological Mision | experts, companies | Administrative costs | 12296.51
GA 3 |  |  | Total GA 3 | 102908.11
| Activity 3.1 Launching of the project | Implementing team of the Project | Human resources | 9600 | Maintaining of good relationships by partners
| Activity 3.2 Dissemination of results in mass media. | Articles in local, regional and national press | Travel | 7240 | Observance of contractual duties by the selected company in relation to the project.
| Activity 3.3 Development and dissemination of publications | Folders,brochures, banners,and other promotional and advertising materials of the project | Subcontracted services | 77450 | Coordinated efforts and harmony in relationships between project partners
| Activity 3.4 Final Press Conference. | Companies providing transportation, accommodation, meal services | Administrative costs | 6732.31 | Maintaining of good relationships by partners
| Activity 3.5 Radio and TV broadcast | Companies providing publishing services and promotional agencies | Other | 1885.8 | Coordinated efforts and harmony in relationships between project partners
| Activity 3.6 Participation on the European days | Implementing team of the Project |  |  | Maintaining of good relationships by partners
GA 4 |  |  | Total GA 4 | 170869.58
| Activity 4.1 Sittings of the Coordination Committee | Office equipped with furniture and devices | Human resources | 66000 | Coordinated efforts and harmony in relationships between project partners and associates.
| Activity 4.2 On-going project monitoring. | Staff, equipment | Travel | 16560
| Activity 4.3 Evaluation. | National and international experts providing training services | Offices | 21600 | Maintenance of good relationships between partners
|  |  | Subcontracted services | 49400
| Activity 4.4 Audit. | Audit Company | Administrative costs | 11178.38 | Observance of contractual duties by the selected company in relation to the project.
|  |  | Other | 3131.2
|  |  | Equipment and supplies | 3000