Decision

of the Joint Monitoring Committee for

2007 – 2013 Black Sea Basin Joint Operational Programme

Having regard to articles 11, 12 and 13 of the Commission Regulation (EC) No 951/2007 of 9 August 2007 laying down implementing rules for cross-border cooperation programmes financed under Regulation (EC) No 1638/2006 of the European Parliament and of the Council laying down general provisions establishing a European Neighbourhood and Partnership Instrument,

Having regard to section 6.1 of the Black Sea Basin Joint Operational Programme, adopted by the European Commission through the Decision no. 7406/27.11.2008,

In accordance with art.11 of the Rules of Procedure of the Joint Monitoring Committee,

Taking into account:

The addendum request sent by the Beneficiary Regional Environmental Centre Moldova (REC Moldova), project 1.2.3.65777.83 MIS-ETC 175 nr.5751/25.01.2012 - „Raising Public Awareness on Solid Municipal Waste Management in the North-West of the Black Sea Region (Less Waste in the North West)”, in order to extend the implementation period of the Action from 18 months to 21 months, according to the grant contract, art. 7.2.10 Special Conditions (derogation from art. 11.1 General Conditions) and art. 7.2.9 Special Conditions (derogation from art. 9 General Conditions) as well.

The justification for rescheduling the outstanding activities and supporting documents/evidences needed for appraisal as well as the updated indicative Action plan for implementation of the Action, Grant Application Form and Partnership Agreements.

The Explanatory Note drafted by the Beneficiary,

The Joint Monitoring Committee of the Black Sea Basin Joint Operational Programme has adopted, by written decision-making procedure, the following decision:

To approve the extension of the implementation period of the project 1.2.3.65777.83 MIS-ETC 175 nr.5751/25.01.2012 - „Raising Public Awareness on Solid Municipal Waste Management in the North-West of the Black Sea Region (Less Waste in the North West)” from 18 to 21 months up till 2nd of November, 2013.

| CHAIR | SECRETARY |
| --- | --- |
| Iulia HERTZOG Head of Joint Managing Authority Ministry of Regional Development and Public Administration, Romania | Laura BOBÂRNAC Programme Manager Ministry of Regional Development and Public Administration, Romania |
| Date: …..th of June, 2013 | Date: ……th of June, 2013 |