## Slide 1: Developing CBC project ideas
Introduction to problem, stakeholder and objective analyses
Black Sea Basin Programme, Information Seminar
Location, Date

## Slide 2: What do you want to improve?

## Slide 3
WHAT ARE THE PROBLEMS?
  Problem analysis is the initial stage of project identification: your project will adress a common problem (e.g. cross-border pollution) or a missed opportunity (e.g. limited access to external markets), the situation should be improved at the end of the project as compared to before!
  Check that the problem has a cross-border dimension related to the programme priorities!
It is not enough to state there is a problem, you should analyse its causes and related effects
  Describe first the negative situation and do not start straight away finding the solution to the problem, there are usually several ways to solve a problem!
  You need to get an overview of all causes of the problem, though you will only target some of them in your project (other may need to be included in project external risks and assumptions)
Problem analysis

## Slide 4
Problem analysis: building the problem “tree”
CAUSES
EFFECTS

## Slide 5: Who’s affected by the negative situation?

## Slide 6
Stakeholder analysis
WHOSE PROBLEM IS IT?
Analyse who’s affected - directly or indirectly – by the problem or have an interest in it: individuals, groups of people, institutions or firms (local authorities, environment agency, farmers…) = stakeholders
  Check cross-border dimension: are there stakeholders in several countries of the Black Sea Basin?
  Analyse the impact of the problem on various stakeholders: different groups have different concerns, capacities and interests (sometimes conflicting) - these need to be understood and recognized in the process of problem identification
  Consult stakeholders from the beginning and throughout project design!

## Slide 7: What could be the improved situation?

## Slide 8
Objective analysis
WHAT ARE THE OBJECTIVES?
  Negative situations of the problem tree converted into positive achievements = objectives
  Methodological approach to:
  Get an overview of the desired future situation (when all problems are remedied)
  Illustrate means-ends relationship
  Keep the analysis of potential objectives clearly based on adressing a range of identified priority problems
  Provides the basis for the project strategy analysis!

## Slide 9
Objective analysis: building the “objective tree”
MEANS
ENDS

## Slide 10: What change can you bring under ENI CBC?

## Slide 11
Strategy analysis
DEFINING THE SCOPE OF YOUR PROJECT IDEA
  Shall all identified problems/objectives be tackled or only a few?
What objective(s) cannot be reached acting only on a national/regional/local level and needs CBC?
  What can realistically be afforded within the Black Sea Basin call financial limits?
  Will it contribute to programme indicators?
  How does it build upon previous/current/planned actions in this field? Possible complementarities/synergies/overlaps? Scope for replication?

## Slide 12: Who’s affected by the desired change or can contribute to it?

## Slide 13
Stakeholders analysis
Stakeholders
Who will benefit?
Who will loose out?
Directly (target groups)
Indirectly/in the long term (final beneficiaries)
What is their capacity and motivation to bring a change?
What are possible actions to address their needs and interest?

## Slide 14: Let’s practice on problem and objective analysis for the Black Sea Basin Programme priorities!

## Slide 15
Problem analysis – Work group per priority
Brainstorm main cross border problems related to the priority and select one individual focal problem – write on yellow card
Identify related problems to this focal problem – write on yellow cards
Establish hierarchy of causes and effects – stick accordingly the cards on the flipchart paper and draw arrows from causes to effects
Identify who’s affected by each problem – write on pink cards and stick next to each related problem
  Think about existing problems, not future or imagined ones!
  The position of the problem in the hierarchy does not indicate its importance!
  A problem is not the absence of a solution, but a negative situation (e.g. “crops are infested with pests” is a problem, “no pesticides are available” is not)!

## Slide 16
Objective analysis – Work group per priority
Reformulate all negative situations of the problems analysis into positive situations that are desirable and realistically achievable – write on green cards
Organise on the flipchart paper accordingly at the same line as appropriate problem
Check the means-ends relationships to ensure validity and completeness of the hierarchy: if necessary revise statements, add new objectives (means) if relevant to achieve the objective at the next higher level, delete objectives which do not seem suitable or necessary
  Assess impact on stakeholders (positive-negative, involvement realistic?) - write on pink cards and stick next to the related objective
  Check complementarities with other relevant initiatives in the same field (e.g. national/regional policies, other EU funded programmes…) – write on blue cards and stick next to the related objective